## V1
Project Development and Completion Tracker
Porject ID: 05
Project Start Date: 02-08-2023 Project End Date: 31-11-2023
Porject Descreption: Alzhemiers Disease Prediction using Deep Learning.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members | Shaaz Mukadam | Project Lead | Project Development Student Team Memebers | Shaaz Mukadam |  | Team Lead | Project Domain Expert Team Members (Geolife) | Shaaz Mukadam | Lead
| Aadityanarayan Jha | Project Vice Lead |  |  |  | Frond End |  | Aadityanarayan Jha | Vice Lead
| Vishal Sakale | Project Member |  | Aadityanarayan Jha |  | Team Lead |  | Vishal Sakale | Project Member
| Pratham Desai | Project Member |  |  |  | Front/Back End |  | Pratham Desai | Project Member
|  |  |  | Vishal Sakale |  | Team Lead
Back End
|  |  |  | Pratham Desai |  | Front End
Epic: | As a aged person , I should check that im having alzhemier's disease or not?
Story 1: | Prediction of alzhemiers disease on different dataset
Story 2:
Story 3:
Task1: | Selected the topic and then we selected the domain for the choosed topic.
Task2: | So as we choosed Deep Learning Technology, after choosing deep learning we browsed multiple research paper to get idea about which dataset is best for prediction ,etc.
Task3: | Started Learning Deep Learning.
Task4: | After completing the course we started with the actual implementation , for that we took dataset from kaggle
Task5: | Successfully Implemeted model.
Task6:
Acceptance Criteria:
1 | Yes, we implemented CNN model on the dataset
2 | ADNI dataset
3 | We got the accuracy of 93%.
4
5
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 0 | Study on research paper of alzhemiers disease. | Feature fusion Heuristic methods · | Complete | Shaaz , Aditrayana | 2023-08-03 | 2023-08-20 | 2023-08-03 | 2023-08-18 | 100% | Not Started | Medium
|  | VGG16 using deep learning | Complete | Pratham , Vishal | 2023-08-03 | 2023-08-20 | 2023-08-03 | 2023-08-18 | 100%
| Identified Dataset | OASIS , ADNI , indgov | Completed | Shaaz , Aditrayana | 2022-02-03 | 2022-02-12 | 2023-08-03 | 2023-08-03 | 100% | In Progress | Low
|  | kaggle alzhemiers disease | Completed | Pratham , Vishal | 2021-10-20 | 2022-02-12 | 2023-08-03 | 2023-08-03 | 100%
| Designed system Architecture. | Created system architecture using figma | Completed | Shaaz , Aditrayana | 2022-02-03 | 2022-02-12 | 2023-08-03 | 2023-08-03 | 100% | Complete | High
|  |  | Completed | Pratham , Vishal | 2021-10-20 | 2022-02-12 | 2023-08-03 | 2023-08-03 | 100%
Sprint 1 | Study on different model of deep learning. | Purshaed a course from Udemy and learned different type of model in deep learning | Completed | Shaaz , Aditrayana | 2021-10-20 | 2021-12-07 | 2023-08-03 | 2023-08-03 | 100% | On Hold
| Choosen CNN model for the disease prediction | We choose CNN model for the prediction of the disease | Completed | Pratham , Vishal | 2023-08-03 | 2023-08-03 | 2023-08-03 | 2023-08-03 | 100% | Overdue
| Implementation using CNN model. | Implemented on google colab | Completed | Shaaz , Aditrayana | 2023-09-28 | 2023-08-03 | 2023-08-03 | 2023-08-03 | 100%
Sprint 2 | Uploded Dataset and Implemented Using Dataset. | Firstly we uploded datset on google colab and run it | Completed | Pratham , Vishal | 2023-09-28 | 2023-10-01 | 2023-10-01 | 2023-10-01 | 100%
| Trainned model | Trainned using cnn model and using various libraries of python | Completed | Shaaz , Aditrayana | 2023-10-02 | 2023-11-01 | 2023-10-02 | 2023-10-29 | 100%
| Test / Validate Model | Finally we tested the model | Completed | Shaaz , Aditrayana | 2023-10-02 | 2023-11-01 | 2023-10-02 | 2023-10-29 | 100%
0
0

## Version 2
Project Development and Completion Tracker
Porject ID: Version 2
Project Start Date: 15-03-2021 Project End Date:
Porject Descreption: Android and ios application for farmers to monitor growth of crop, fertilizer recomendation and providing regionwise market analysis of crop. (V1) Along with crop growth calendar and stagewise NPK requirement calculation.
| Name of Team member | Designation |  | Name of Students |  | Role |  | Name | Designation
Project Architech Team Members |  |  | Project Development Student Team Memebers |  |  | Team Lead | Project Domain Expert Team Members (Geolife)
Frond End
Team Lead
Front/Back End
Team Lead
Back End
Front End
Epic: | As a farmer, I should know fertilizer requirement for my crop in my region to fulfill N,P,K.
Story 1: | As a farmer, I should get growth calendar of crop.
Story 2: | As a farmer, I should know growth wise activity reminder of crop.
Story 3: | As a farmer, need stagewise reccomendation of fertilizer to fulfil N,P,K requiremnt of my crop.
Task1: | Design a layout to select crop.
Task2: | Design a layout to select sowing date for crop.
Task3: | Design a layout which will display crop calendar contaiinng stages like watering, pestisides, fertilizer, etc.
Task4: | Create reminders in calendar along with details of each stage with its all possible recommendation.
Task5: | Incorporate NPK requirement to growth calendar stagewise by considering soil contribution and efficacy of crop.
Acceptance Criteria:
1 | Farmer can select crop for sowing in the season out of list with images.
2 | Farmer can select date of sowing with validation.
3 | Completion of stages of crop in calendar are visibille and reminders get pop-up.
4 | When task get completed by farmer, he can input completion of task.
5 | Farmer can view NPK stages requirement and add completion status.
Sprint No. | Task Name | Sub Tasks | Task Status | Assigned To | Assigned Date | Deadline | Start Date | Completion Date | Completion Status
Sprint 1 | Design a layout to select crop. | Creating layout of showing crop categories | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Not Started | Medium
|  | After selecting category, show crop images and selection. | Complete | Sunny Yadav, Sumeet Sapkal |  | 25-10-2021 |  |  | 100%
| Design a layout to select sowing date for crop. | Use calendar API in app. | Complete | Siddhant Oswal, Simon Singh |  | 25-10-2021 |  |  | 100% | In Progress | Low
|  | Show sowing date selction in app. | Complete | Simon Singh, Siddhant Oswal |  | 25-10-2021 |  |  | 100%
| Design a layout which will display crop calendar containg stages like watering, pestisides, fertilizer, etc. | Create database of all crops containg growth stages, watering, pestiside and fertilizer dates. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 50% | Complete | High
|  | Create reminders and display details and recomendation of each stage. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
| When task get completed by farmer, he can input completion of task. | Activity will be in active state till completion. User will make it completed by input. | Not Started | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0%
|  | User inputs get reflected in database as well. | On Hold | Rutvi Nair, Vipul Kumar Singh, Varun Kapse |  | 25-10-2021 |  |  | 0% | On Hold
| Farmer can view NPK stages requirement and add completion status. | NPK requirement calculation as per growth stage. | Complete | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 100% | Overdue
|  | Include these data in calendar. | In Progress | Sunny Yadav,Sumeet Sapkal |  | 25-10-2021 |  |  | 20%

## Student Team
STUDENT INTERN LIST
Sr. No. | Name of Inern | Email Address | Contact | class | Domain (Web, App, Backend)
1 | Prajwal Sah | prajwalsah212@gmail.com | 7776012981 | FY IT DA | ML
2 | Shriya Dilliwale | anitashriya12@gmail.com | 7559361354 | FY IT DA | Flutter, ML | Version 1
3 | Nikhil Chavan | nikhilchavan407@gmail.com | 8369686747 | FY IT - CORE | Flutter | Version 1
4 | Vipul Kumar Singh | vipulkumarbhore@gmail.com | 7764059016 | FY IT - CORE | Flutter | Version 2
5
6
8
9
10
3 | Anjali Bhatt | anjalibhatt601@gmail.com | 830811254 | FY CSE Core 2 | Flutter, ML | Version 1
4 | Shruti Singasane | singasane.shruti2001@gmail.com | 8652233102 | FY CSE Core 2 | Flutter, ML | Version 1
5 | Rushil Jain | rushiljain2001@gmail.com | 9371775841 | FY CSE IS 1 | Flutter, ML | Version 1
7 | Sumeet Sapkal | sumeetspkl@gmail.com | 9112156784 | FY CSE | Flutter, MySQL | Version 2
8 | Sunny Yadav | sunnyyadavtheone@gmail.com | 7878964402 | FY CSE | Flutter, MySQL | Version 2
9 | Siddhant Oswal | oswalsiddhant2001@gmail.com | 8329979013 | FY CSE | Flutter | Version 2
10 | Simon Singh | simonsinghdomain@gmail.com | 7470659108 | FY CSE | Flutter | Version 2
11 | Varun Kapse | varunkapse07@gmail.com | 8830624385 | FY IT - PASSED | ML | Version 2
13 | Rutvi Nair | rutvinar305098@gmail.com | 8141393918 | TY CSE IS 1 | Flutter | Version 2